Contract Analysis - Checklist

| # | Item | Result / Reference to Contract / Remarks |
| --- | --- | --- |
| 1 | Contractual Relationships - Who is directly involved in / signing the contract? - Contractual relationships? (graphical representation) - Customer-Supplier relationship? - Customer-Supplier-Engineer relationship? - Third parties, whose deliverables or services are included? - If yes - who are the third parties? |  |
| 2 | Scope of Contract: Deliverables and Services - Description of deliverables? - Description of services? - Functional description? - List of requirements? - Specification? |  |
| 3 | Deliverables and Services to be Provided by the Customer in Advance - Preliminary construction work? - Supply of material? - Access to site / building? - Storage on site possible? - Deadlines for deliverables and services to be provided in advance? |  |
| 4 | Scope Changes - Change process for deliverables? - Change process for services? - Design freeze procedures? - Change of acceptance procedures (cf. #10)? - Auxiliary obligations and due diligence? - Changes of general technical data and information? - Periods of notification? - Form of change requests? - Form of change orders? - Other services if not included in the deliverables and services? |  |
| 5 | Contract Documents - List of requirements? - Specifications? - Drawings? - Design freeze documents? - Technical standards? - Acceptance test documents (cf. #10)? - General terms and conditions? |  |
| 6 | Prices - Currency? - Value Added Tax (VAT)? - Price adjustment? - Wage / salary rises? - Material procurement costs? - Cost of energy? - Cost of fuel? - Taxes? - Other charges? |  |
| 7 | Terms and Conditions of Payment - Fixed payment milestones? - Event driven payment milestones? - Penalty in case of delay? - Penalty in case of default? - Due date? - Interest after due date? - Publishing annual financial statements? |  |
| 8 | Taxes and Charges - Taxes? - Charges? - Fees? - Dues? - Clearing? |  |
| 9 | Schedule: Delivery Periods - Deadlines defined? - Start of the periods, unless defined by calendar date? - Changes in delivery periods in the event of modifications, holdups, force majeure? - Delays: Definition, consequences of delays? - Involvement of the customer in case of a delay? |  |
| 10 | Acceptance - Prerequisites for acceptance? - Acceptance procedure? - Participation in acceptance procedure? - Acceptance certificates? - Consequences of unsuccessful acceptance? - Consequences of successful acceptance? |  |
| 11 | Claims - Claim process defined? - Procedure of claim settlement defined? - Escalation steps of dispute resolution? - Periods of notification? - Form of claims? |  |
| 12 | Warranty - Legal consequences in case of defect(s)? - Complaint by customer? - Time allotted to rectify defect(s)? - Legal consequences if repair of defects fails or is refused? - Statutory limitations on warranty claims? - Start of period? - Duration of period? - Formal request (receipt)? - Resulting costs? |  |
| 13 | Liability - Exemption from liability? - Limitation of liability? - Unlimited liability? |  |
| 14 | Reservation of ownership - Agreement on reservation of ownership? - Ordering party's mandatory insurance for reserved deliveries? - Prohibition of pledges? |  |
| 15 | Applicable law |  |
| 16 | Place of Fulfillment and Jurisdiction - Place of fulfillment? - Place of jurisdiction? - Priority for one language if contracts are in various languages? |  |
| 17 | Non-applicability of individual provisions - Safeguarding clause? |  |
| 18 | Other Items not Included in #1 through #16, Miscellaneous |  |