## data
Project: | Project Name
|  | Reporting Plan: |  | every | 28 | days
|  |  | Plan | Actuals
Milestone Name | Milestones |  | 2009-07-01 | 2009-07-01 | 2009-07-29 | 2009-08-26 | 2009-09-23 | 2009-10-21 | 2009-11-18 | 2009-12-16 | 2010-01-13 | 2010-02-10 | 2010-03-10 | 2010-04-07 | 2010-05-05 | 2010-06-02 | 2010-06-30 | 2010-07-28 | 2010-08-25 | 2010-09-22 | 2010-10-20 | 2010-11-17 | 2010-12-15 | 2011-01-12 | 2011-02-09 | 2011-03-09 | 2011-04-06 | 2011-05-04 | 2011-06-01 | 2011-06-29 | 2011-07-27 | 2011-08-24 | 2011-09-21 | 2011-10-19 | 2011-11-16 | 2011-12-14 | 2012-01-11 | 2012-02-08 | 2012-03-07 | 2012-04-04 | 2012-05-02 | 2012-05-30 | 2012-06-27 | 2012-07-25 | 2012-08-22 | 2012-09-19 | 2012-10-17 | 2012-11-14 | 2012-12-12 | 2013-01-09 | 2013-02-06 | 2013-03-06 | 2013-04-03 | 2013-05-01 | 2013-05-29 | 2013-06-26 | 2013-07-24 | 2013-08-21 | 2013-09-18 | 2013-10-16 | 2013-11-13 | 2013-12-11 | 2014-01-08 | 2014-02-05 | 2014-03-05 | 2014-04-02 | 2014-04-30 | 2014-05-28 | 2014-06-25 | 2014-07-23 | 2014-08-20 | 2014-09-17 | 2014-10-15 | 2014-11-12 | 2014-12-10 | 2015-01-07 | 2015-02-04 | 2015-03-04 | 2015-04-01 | 2015-04-29 | 2015-05-27 | 2015-06-24 | 2015-07-22 | 2015-08-19 | 2015-09-16 | 2015-10-14 | 2015-11-11 | 2015-12-09 | 2016-01-06 | 2016-02-03 | 2016-03-02 | 2016-03-30 | 2016-04-27 | 2016-05-25 | 2016-06-22 | 2016-07-20 | 2016-08-17 | 2016-09-14 | 2016-10-12 | 2016-11-09 | 2016-12-07 | 2017-01-04 | 2017-02-01 | 2017-03-01 | 2017-03-29 | 2017-04-26 | 2017-05-24 | 2017-06-21 | 2017-07-19 | 2017-08-16 | 2017-09-13 | 2017-10-11 | 2017-11-08 | 2017-12-06 | 2018-01-03 | 2018-01-31 | 2018-02-28 | 2018-03-28 | 2018-04-25 | 2018-05-23 | 2018-06-20 | 2018-07-18 | 2018-08-15 | 2018-09-12 | 2018-10-10 | 2018-11-07 | 2018-12-05 | 2019-01-02 | 2019-01-30 | 2019-02-27 | 2019-03-27 | 2019-04-24 | 2019-05-22 | 2019-06-19 | 2019-07-17
name_20 | M20
name_19 | M19
name_18 | M18
name_17 | M17
name_16 | M16
name_15 | M15
name_14 | M14
name_13 | M13
name_12 | M12
name_11 | M11
name_10 | M10
name_9 | M9
name_8 | M8
name_7 | M7
name_6 | M6
name_5 | M5
name_4 | M4 |  | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31 | 2010-05-31
name_3 | M3 |  | 2010-02-28 | 2010-02-28 | 2010-02-28 | 2010-02-28 | 2010-02-28
name_2 | M2 |  | 2009-11-30 | 2009-11-30 | 2009-12-31 | 2009-12-31 | 2009-12-31
name_1 | M1 |  | 2009-09-30 | 2009-09-30 | 2009-10-31 | 2009-10-31 | 2009-10-31
Project Start | M0 |  | 2009-07-01 | 2009-07-01
|  | X-Axis / Y-Axis, Minimum: | 39995
Insert milestone names, planned milestone dates, reporting plan period, and reported milestone dates into this worksheet "data".
View result on worksheet "chart".
If you want to input a new schedule, then observe cell E30. As soon as you have a new date for M0, Project Start, the value of E30 changes. This is the new value for re-formatting the graph: E30 contains the minimum value for x- and y-axis. (The maximum values of both axes have to be changed as well, so that the resulting picture is read-able, and "looks nice".)

## chart
Project: | Project Name
Reporting Date: | 2009-09-23
Milestone Name | Milestones
name_20 | M20
name_19 | M19
name_18 | M18
name_17 | M17
name_16 | M16
name_15 | M15
name_14 | M14
name_13 | M13
name_12 | M12
name_11 | M11
name_10 | M10
name_9 | M9
name_8 | M8
name_7 | M7
name_6 | M6
name_5 | M5
name_4 | M4
name_3 | M3
name_2 | M2
name_1 | M1
Project Start | M0